## Front_cover
These statements are the primary sources of information about Highways England’s performance in accordance with the ORR Monitoring Guidelines1

Notes
- Where applicable, regional data will be developed over RIS2 and Highways England will work with the ORR on making this information available (link to information available to be provided) / - Detailed information regarding efficiency delivery and statement in relation to inflationary impact will be contained in the published Highways England Efficiency Report

Contents

Performance Specification statements
PS1	Improving safety for all
PS2	Providing fast and reliable journeys
PS3	A well maintained and resilient network
PS4	Delivering better environmental outcomes
PS5	Meeting the needs of all road users
PS6	Achieving efficient delivery
Investment Plan statements
IP1	Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
IP2	RIS 3 Development Pipeline
IP3	Designated Funds
IP4	Renewal Volume Reporting
IP5	Maintenance Delivery Reporting
Financial Performance statements
F1	Total income and expenditure
F2	Regional resource income and expenditure
F2.1	Resource income and projects expenditure
F2.2	Analysis of protocols expenditure
F3	Capital expenditure
F3.1	Enhancement expenditure
F3.2	Regional capital income and expenditure

Annual Statement

1 https://www.orr.gov.uk/sites/default/files/om/monitoring-reporting-guidelines-for-highways-england-for-road-period-2.pdf

## PS1-Improving_safety_for_all
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS1: Improving safety for all			For a definition of the metric and parameters for measuring and monitoring safety performance see Highways England’s Operational Metrics Manual
Performance specification
	Source of Target	Actual	Target	KPI/PI	Difference (Actual vs Target)					Notes
KPI

The number of people killed or seriously injured on the SRN.
Ongoing reduction in the number of people killed or seriously injured on the SRN as reported in STATS19 to support a decrease of at least 50% by the end of 2025 against the 2005-09 average baseline. A +/- variance of 5% each year has been agreed with DfT Road User Safety Division to support this target.					The number of people killed or seriously injured on the SRN.
Note: baseline will change each year as adjusted figures are produced
2005-09 baseline	Performance Specification

2015	Unadjusted			KPI
	Adjusted
2016	Unadjusted			KPI
	Adjusted
2017	Unadjusted			KPI
	Adjusted
2018	Unadjusted			KPI
	Adjusted
2019	Unadjusted			KPI
	Adjusted
2020	Adjusted			KPI	0
2021	Adjusted			KPI	0
2022	Adjusted			KPI	0
2023	Adjusted			KPI	0
2024	Adjusted			KPI	0
2025	Adjusted			KPI	0

PIs

The total number of people killed or injured on the SRN.
Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer.					The total number of people killed or injured on the SRN
2015	Performance Specification		N/A	PI	N/A
2016	Performance Specification		N/A	PI	N/A
2017	Performance Specification		N/A	PI	N/A
2018	Performance Specification		N/A	PI	N/A
2019	Performance Specification		N/A	PI	N/A
2020	Performance Specification		N/A	PI	N/A
2021	Performance Specification		N/A	PI	N/A
2022	Performance Specification		N/A	PI	N/A
2023	Performance Specification		N/A	PI	N/A
2024	Performance Specification		N/A	PI	N/A
2025	Performance Specification		N/A	PI	N/A

The number of non-motorised and motorcyclist users killed or injured on the SRN.
The total number of pedestrian, pedal cyclist, motorcyclist and equestrian casualties on the SRN. Disaggregation will be provided by road user group to assist understanding of the PI but are not considered PIs in their own right.					The number of non-motorised and motorcyclist users killed or injured on the SRN.
2015	Performance Specification		N/A	PI	N/A
2016	Performance Specification		N/A	PI	N/A
2017	Performance Specification		N/A	PI	N/A
2018	Performance Specification		N/A	PI	N/A
2019	Performance Specification		N/A	PI	N/A
2020	Performance Specification		N/A	PI	N/A
2021	Performance Specification		N/A	PI	N/A
2022	Performance Specification		N/A	PI	N/A
2023	Performance Specification		N/A	PI	N/A
2024	Performance Specification		N/A	PI	N/A
2025	Performance Specification		N/A	PI	N/A

The number of motorcyclist users killed or injured on the SRN.					The number of motorcyclist users killed or injured on the SRN.
2015	Performance Specification		N/A	N/A	N/A
2016	Performance Specification		N/A	N/A	N/A
2017	Performance Specification		N/A	N/A	N/A
2018	Performance Specification		N/A	N/A	N/A
2019	Performance Specification		N/A	N/A	N/A
2020	Performance Specification		N/A	N/A	N/A
2021	Performance Specification		N/A	N/A	N/A
2022	Performance Specification		N/A	N/A	N/A
2023	Performance Specification		N/A	N/A	N/A
2024	Performance Specification		N/A	N/A	N/A
2025	Performance Specification		N/A	N/A	N/A

The number of cyclists killed or injured on the SRN.					The number of cyclists killed or injured on the SRN.
2015	Performance Specification		N/A	N/A	N/A
2016	Performance Specification		N/A	N/A	N/A
2017	Performance Specification		N/A	N/A	N/A
2018	Performance Specification		N/A	N/A	N/A
2019	Performance Specification		N/A	N/A	N/A
2020	Performance Specification		N/A	N/A	N/A
2021	Performance Specification		N/A	N/A	N/A
2022	Performance Specification		N/A	N/A	N/A
2023	Performance Specification		N/A	N/A	N/A
2024	Performance Specification		N/A	N/A	N/A
2025	Performance Specification		N/A	N/A	N/A

The number of pedestrians killed or injured on the SRN.					The number of pedestrians killed or injured on the SRN.
2015	Performance Specification		N/A	N/A	N/A
2016	Performance Specification		N/A	N/A	N/A
2017	Performance Specification		N/A	N/A	N/A
2018	Performance Specification		N/A	N/A	N/A
2019	Performance Specification		N/A	N/A	N/A
2020	Performance Specification		N/A	N/A	N/A
2021	Performance Specification		N/A	N/A	N/A
2022	Performance Specification		N/A	N/A	N/A
2023	Performance Specification		N/A	N/A	N/A
2024	Performance Specification		N/A	N/A	N/A
2025	Performance Specification		N/A	N/A	N/A

The number of equestrians killed or injured on the SRN.					The number of equestrians killed or injured on the SRN.
2015	Performance Specification		N/A	N/A	N/A
2016	Performance Specification		N/A	N/A	N/A
2017	Performance Specification		N/A	N/A	N/A
2018	Performance Specification		N/A	N/A	N/A
2019	Performance Specification		N/A	N/A	N/A
2020	Performance Specification		N/A	N/A	N/A
2021	Performance Specification		N/A	N/A	N/A
2022	Performance Specification		N/A	N/A	N/A
2023	Performance Specification		N/A	N/A	N/A
2024	Performance Specification		N/A	N/A	N/A
2025	Performance Specification		N/A	N/A	N/A

Number of injury collisions on the SRN
The total number of collisions recorded that resulted in at least one injury (of any severity) on the SRN.					Number of injury collisions on the SRN
2020	Performance Specification		N/A	PI	N/A
2021	Performance Specification		N/A	PI	N/A
2022	Performance Specification		N/A	PI	N/A
2023	Performance Specification		N/A	PI	N/A
2024	Performance Specification		N/A	PI	N/A
2025	Performance Specification		N/A	PI	N/A

The accident frequency rate for Highways England staff
The accident frequency rate for Highways England staff based on Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.					The accident frequency rate for Highways England staff
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

The accident frequency rate for Highways England supply chain staff
The accident frequency rate for Highways England supply chain staff based on Reporting of Injuries Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.					The accident frequency rate for supply chain staff
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

The % of traffic using iRAP 3* or above rated roads
IRAP based road safety investigations, developed in conjunction with the department, to feed into subsequent route strategies. Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer. We are committed to ensure that 90% of travel on our roads is 3* rated or higher by 2020. The latest data indicates that 95% of travel on our roads is on 3-star rated roads or above which exceeds the target set in our delivery plan / The percentage of travel on roads with an International Road Assessment Programme (iRAP) safety rating of 3-star or better calculated using the latest version of the iRAP model (version 3.02).					The % of traffic using iRAP 3* or above rated roads
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Commitments

Work with Transport Focus to investigate a rate-based measure for non-motorised user casualties.

1.1 Working with TF, investigate a rate-based measure for non-motorised user casualties
OMM Stages	Milestone

Concept Stage	Q3 2020-21

Feasibility Stage	Q2 2021-22

Development Stage	TBC following review

Validation Stage	TBC following review

iRAP baseline to be established in 2021, and 2025 forecast developed, based on latest iRAP methodology.

1.2 iRAP baseline to be established in 2021, and 2025 forecast and development, based on latest IRAP methodology
OMM Stages	Milestone

Concept Stage	N/A

Feasibility Stage	N/A

Development Stage	Q2 2021-22

Validation Stage	N/A

Notes and commentary

## PS2-Fast_and_reliable
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS2: Providing fast and reliable journeys		For a definition of the metric and parameters for measuring and monitoring User satisfaction see Highways England’s Operational Metrics Manual
Performance specification
	Source of Target	Actual	Target	KPI/PI	Difference (Actual vs Target)					Notes
KPI

Average Delay					Average Delay (Seconds per veh per mile)
Average delay to road users calculated as the difference between the observed travel time and the speed limit travel time.
Ambition – Performance to be no worse at the end of Road Period 2 than it is at the end of Road Period 1. Highways England will be required to demonstrate how it has acted to reduce delays in support of this ambition. This KPI does not have a target.
2020-21	Performance Specification		Ambition	KPI
2021-22	Performance Specification		Ambition	KPI
2022-23	Performance Specification		Ambition	KPI
2023-24	Performance Specification		Ambition	KPI
2024-25	Performance Specification		Ambition	KPI

					Network availability
Network availability
The percentage of the strategic road network that is free from lane closures due to roadworks.
Target: Achieve 97.5% lane availability in 2020-21. The existing metric is expected to be replaced during 2020-21 by a new expanded metric. A baseline level of performance for the new metric will be determined in 2020-21 and will be used to set a target covering the remainder of Road Period 2.
2020-21	Performance Specification		97.5%	KPI	-97.5%
2021-22	-			KPI	0.0%
2022-23	-			KPI	0.0%
2023-24	-			KPI	0.0%
2024-25	-			KPI	0.0%

Incident clearance rate					Incident clearance rate
The percentage of incidents on the motorway that impact traffic flow but are cleared in less than one hour.
Target: 86% of motorway incidents cleared within one hour.
2020-21	Performance Specification		86.0%	KPI	-86.0%
2021-22	Performance Specification		86.0%	KPI	-86.0%
2022-23	Performance Specification		86.0%	KPI	-86.0%
2023-24	Performance Specification		86.0%	KPI	-86.0%
2024-25	Performance Specification		86.0%	KPI	-86.0%

PIs

Delay on smart motorways					Delay on smart motorways (seconds per veh per mile)
Average delay to road users on smart motorways calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at upper limit for variable speed limit sections). It is a subset of the Average delay metric.
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Delay from roadworks					Delay from roadworks (mins per hr travelled)
This metric measures the additional journey time during roadworks for all vehicle types, compared to an average benchmark journey time measured before the roadworks were in place. Calculated as average annual delay (minutes per hour travelled).
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Journey time reliability					Journey time reliability (Seconds per veh per mile)
The average difference between the observed travel time and the profile (typical) travel time.
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Delay on gateway routes					Delay on gateway routes (Seconds per veh per mile)
Average delay to users of gateway routes. Delay is calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at the speed limit). It is a subset of the average delay metric.
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Average speed					Average speed (miles per hour)
The average speed of vehicles travelling on the strategic road network
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Commitments

Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21

2.1 Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21
OMM Stages	Milestone

Concept Stage	-

Feasibility Stage	-

Development Stage	Q3 2020-21

Validation Stage	Q4 2020-21

Working with Transport Focus, investigate the development of new metrics on journey time reliability which reflects more accurately road users’ understanding of reliability, and delay in roadworks.

2.2 Working with TF, investigate the development of the new metrics on journey time reliability which reflects more accurately road users understanding of reliability, and delay in roadworks
OMM Stages	Milestone

Concept Stage	Q3 2020-21

Feasibility Stage	Q2 2021-22

Development Stage	TBC following review

Validation Stage	TBC following review

Investigate new PIs on delays from incidents and delays on the local road/SRN boundary, and an alternative performance measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives.

2.3 Investigate new PIs on delays from incidents &delays on local road/ SRN boundary, & an alternative perf. Measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives
OMM Stages	Milestone

Concept Stage	Q3 2020-21

Feasibility Stage	Q2 2021-22

Development Stage	TBC following review

Validation Stage	TBC following review

Notes and commentary

## PS3-Maintainance_and_resilience
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS3: A well maintained and resilient network		For a definition of the metric and parameters for measuring and monitoring the flow of traffic see Highways England’s Operational Metrics Manual
Performance specification
	Source of Target	Actual	Target	KPI/PI	Difference (Actual vs Target)					Notes
KPIs

Pavement condition					Pavement condition
The percentage of pavement asset that does not require further investigation for possible maintenance. This measure reports on the overall strategic road network condition as a result of deterioration of the pavement network due to time and traffic and restoration of condition from the annual investment in maintenance. / Target: Percentage of the network (as defined by HAPMS, excluding DBFOs) requiring no further investigation to be maintained at 95% or above.

2020-21	Performance Specification		95.0%	KPI	-95.0%
2021-22	Performance Specification		95.0%	KPI	-95.0%
2022-23	-			KPI	0.0%
2023-24	-			KPI	0.0%
2024-25	-			KPI	0.0%

PIs

Structures condition					Structures condition
The condition of Highways England’s structures across the strategic road network.

2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Technology availability					Technology availability
The percentage of time that roadside technology assets are available and functioning. The assets are considered available and functioning if they are not experiencing a service-affecting fault.

2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Drainage resilience					Drainage resilience
The percentage length of carriageway that does not have an observed significant susceptibility to flooding

2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Geotechnical condition					Geotechnical condition
The percentage length of the Highways England’s geotechnical asset that is in good condition based on the ability of the asset to perform its function at the time of inspection (i.e. to support other highways assets).

2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Commitments

Implement the AMDP for RP2 as described above.

3.1 Implement the AMDP for RP2 as described above (in the RIS document)

OMM Stages / milestone
Agree AMDP deliverables for the following financial year: Q4 each year

End of year report: Q1 the following year

End of year review of deliverables: Q2 the following year

Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets

3.2 Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets
OMM Stages	Milestone

Concept Stage	Q3 2020-21

Feasibility Stage	Q2 2021-22

Development Stage	TBC following review

Validation Stage	TBC following review

Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1

3.3 Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1
OMM Stages	Milestone

Concept Stage	-

Feasibility Stage	-

Development Stage	-

Validation Stage	Q4 2021-22

Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised

3.4 Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised
OMM Stages	Milestone

Concept Stage	-

Feasibility Stage	-

Development Stage	Q4 2021-22

Validation Stage	Q3 2023-24

Notes and commentary

## PS4_-_Environment
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS4 Delivering better environmental outcomes		For a definition of the metric and parameters for measuring and monitoring the flow of traffic see Highways England’s Operational Metrics Manual
Performance specification
	Source of Target	Actual	Cumulative	Target	KPI/PI	Difference (Actual vs Target)					Notes
KPIs

Noise
The number of households within mitigated Noise Important Areas where noise has been reduced through Highways England designated fund projects.
Target: 7,500 households benefitting from noise reduction in mitigated Noise Important Areas (defined by the Department for Environment, Food and Rural Affairs (DEFRA)) using funding from the environment and wellbeing designated fund during Road Period 2
2020-21	Performance Specification		0	7500	KPI	-7500
2021-22	Performance Specification		0	7500	KPI	-7500
2022-23	Performance Specification		0	7500	KPI	-7500
2023-24	Performance Specification		0	7500	KPI	-7500
2024-25	Performance Specification		0	7500	KPI	-7500
Annual					Cumulative
					Biodiversity (Biodiversity Unit)
Biodiversity
Deliver no net loss of biodiversity, measured using an industry standard way of measuring biodiversity changes referred to as the biodiversity metric.
Target: Achieve no net loss of biodiversity, across all Highways England activities, by the end of Road Period 2.
2020-21	-		N/A	No net loss	KPI
2021-22	-		N/A	No net loss	KPI
2022-23	-		N/A	No net loss	KPI
2023-24	-		N/A	No net loss	KPI
2024-25	-		N/A	No net loss	KPI

Air Quality
The number of strategic road network links in exceedance of the legal nitrogen dioxide (NO2) limits as set by the European Union and accepted by the government.
Bring links agreed with the department and based on the Pollution Climate Mapping model into compliance with legal NO2 limits in the shortest timescales possible

Highways England carbon emissions					Highways England Carbon Emissions
Target: Reduce Highways England’s carbon emissions as a result of electricity consumption, fuel use and other day-to-day operational activities during RP2, to levels defined by baselining and target setting activities in 2020-21. This metric will become operational from 1 April 2021.
2020-21	-		N/A		KPI	0
2021-22	-		N/A		KPI	0
2022-23	-		N/A		KPI	0
2023-24	-		N/A		KPI	0
2024-25	-		N/A		KPI	0

PIs
					Supply Chain Carbon Emissions
Supply Chain Carbon emissions
The carbon footprint associated with Highways England’s supply chain and also normalised by the volume of work undertaken.
		Absolute	Normalised
2020-21	Performance Specification			N/A	PI	N/A
2021-22	Performance Specification			N/A	PI	N/A
2022-23	Performance Specification			N/A	PI	N/A
2023-24	Performance Specification			N/A	PI	N/A
2024-25	Performance Specification			N/A	PI	N/A

					Heritage assets condition
Condition of Cultural Heritage assets
The overall condition of the culturally significant assets owned by Highways England.
2020-21	Performance Specification		N/A	N/A	PI	N/A
2021-22	Performance Specification		N/A	N/A	PI	N/A
2022-23	Performance Specification		N/A	N/A	PI	N/A
2023-24	Performance Specification		N/A	N/A	PI	N/A
2024-25	Performance Specification		N/A	N/A	PI	N/A

Water Quality					Water Quality (km)
The length of watercourse enhanced through the mitigation of medium, high, and very high risk outfalls as well as through other enhancements, for example river retraining/rewilding.
2020-21	Performance Specification		N/A	N/A	PI	N/A
2021-22	Performance Specification		N/A	N/A	PI	N/A
2022-23	Performance Specification		N/A	N/A	PI	N/A
2023-24	Performance Specification		N/A	N/A	PI	N/A
2024-25	Performance Specification		N/A	N/A	PI	N/A

					Litter
Litter
The percentage of the strategic road network where litter is graded at A or B as defined in the Code of practice on litter and refuse 2006.
2020-21	Performance Specification		N/A	N/A	PI	N/A
2021-22	Performance Specification		N/A	N/A	PI	N/A
2022-23	Performance Specification		N/A	N/A	PI	N/A
2023-24	Performance Specification		N/A	N/A	PI	N/A
2024-25	Performance Specification		N/A	N/A	PI	N/A

Commitments

Highways England carbon emissions KPI: Reduce Highway England's carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselineing & target setting activities in 2020-21

4.1 Highways England carbon emissions KPI: Reduce Highway England's carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselineing & target setting activities in 2020-21
OMM Stages	Milestone

Inventory and asset register update; data collation including project action plans	Q3 2020-21

Start of formal sign-off process of new metric and target with DfT	Q4 2020-21

Completion of validation; approvals of target	Q4 2020-21

Validation Stage	Q4 2020-21

Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach.

4.2 Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach
OMM Stages	Milestone

Concept Stage	Q3 2020-21

Feasibility Stage	Q2 2021-22

Development Stage	TBC following review

Validation Stage	TBC following review

Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on Highways England work, and associated reporting requirements. A more detailed timetable for these investigations will be produced in Year 1 of RP2, as well as potential implementation opportunities identified by that stage.

4.3 Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on highways England work, and associated reporting requirements. A more detailed timetablefor these investigations will be produced in year 1 od RP2, as well as potential implimentation oppertunities identified by that stage.
OMM Stages	Milestone

Concept Stage	Q3 2020-21

Feasibility Stage	Q2 2021-22

Development Stage	TBC following review

Validation Stage	TBC following review

Notes and commentary

## PS5-Needs_of_all_road_users
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS5: Meeting the needs of all road users				For a definition of the metric and parameters for measuring and monitoring performance regarding vulnerable users see Highways England’s Operational Metrics Manual
Performance specification
	Source of Target	Actual	Target	KPI/PI	Difference (Actual vs Target)					Notes
KPIs

Road user satisfaction					Road user satisfaction
The percentage of drivers who are satisfied with their journey on the strategic road network as measured by the Strategic Roads User Survey (SRUS) conducted by Transport Focus.
Target: Achieve an 82% road user satisfaction score in 2020-21 and 2021-22, with year-on-year increases in the following years. The exact targets for 2022-23, 2023-24, and 2024-25 will be set during 2021-22.

2020-21	Performance Specification		82.0%	KPI	-82.0%
2021-22	Performance Specification		82.0%	KPI	-82.0%
2022-23				KPI
2023-24				KPI
2024-25				KPI

Roadworks information timeliness and accuracy					Roadworks information timeliness and accuracy
The percentage of overnight road closures that are accurately notified by Highways England seven days in advance. A correctly notified road closure is one that commences within +/- 1 hour of the start time stated 7 days in advance on the Network Occupancy Management System (NOMS).
Target: Achieve 90% accuracy of roadworks information seven days (rolling) in advance of works by 2024-25, with an increasing trajectory of improvement through Road Period 2 from the level of performance achieved by the end of Road Period 1

2020-21	Performance Specification			KPI
2021-22	Performance Specification			KPI
2022-23	Performance Specification			KPI
2023-24	Performance Specification			KPI
2024-25	Performance Specification		90.0%	KPI	-90.0%

PIs

Timeliness of information provided to road users through electronic signage					Timeliness of information provided to road users through electronic signage (Mins/Secs)
The average median time to set signs and signals on (all) motorways after Highways England has received notification of an incident, that requires signs and signals to be manually set.

2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Ride Quality					Ride Quality
This measure reports the ride quality for the strategic road network using a subset of the pavement condition metric condition parameters. It is represented by the percentage of pavement asset delivering ride quality consistent with the 3m Enhanced Longitudinal Profile Variance (ELPV) value in Highways England’s standards, which is based on engineering factors and driver comfort. / Percentage of the network (as defined by HAPMS, excluding DBFOs) where 3m ELPV is deemed to be category 2 and better, in accordance with the road condition standard, HD29.
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Working with local highways authorities to review diversion routes for unplanned events.					Working with LHA to review diversion routes for unplanned events
2020-21	Performance Specification		N/A	PI	N/A
2021-22	Performance Specification		N/A	PI	N/A
2022-23	Performance Specification		N/A	PI	N/A
2023-24	Performance Specification		N/A	PI	N/A
2024-25	Performance Specification		N/A	PI	N/A

Commitments

Work with Transport Focus to develop satisfaction surveys for cyclists and pedestrians that can be used, if possible, as the basis of a PI later in RP2.

5.1 Work with TF to develop satisfaction surveys for cyclists & pedestrians that can be used, if possible, as the basis of a PI later in RP2
OMM Stages		Milestone

Concept Stage		Transport focus led commitment

Feasibility Stage		Transport focus led commitment

Development Stage		Transport focus led commitment

Validation Stage		Transport focus led commitment

Work with Transport Focus to develop satisfaction surveys for logistics and coach managers that can be used, if possible, as the basis of a PI later in RP2.

5.2 Work with TF to develop satisfaction surveys for logistics & coach managers that can be used, if possible, as the basis of a PI later in RP2
OMM Stages		Milestone

Concept Stage		Transport focus led commitment

Feasibility Stage		Transport focus led commitment

Development Stage		Transport focus led commitment

Validation Stage		Transport focus led commitment

Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22.

5.3 Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22
OMM Stages		Milestone

Concept Stage		N/A

Feasibility Stage		N/A

Development Stage		N/A

Validation Stage		Q4 2021-22

Develop with Transport Focus during RP2 a measure of ride quality which reflects road users’ experience of the network.

5.4 Develop with Transport Focus during RP2 a measure of ride quality which reflects road users' experience of the network
OMM Stages		Milestone

Concept Stage		Q2 2020-21

Feasibility Stage		Q4 2020-21

Development Stage		Q2 2021-22

Validation Stage		Q4 2021-22

Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks.

5.5 Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks
OMM Stages		Milestone

Concept Stage		Q3 2020-21

Feasibility Stage		Q2 2021-22

Development Stage		TBC following review

Validation Stage		TBC following review

Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs.

5.6 Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs
OMM Stages		Milestone

Concept Stage		Q3 2020-21

Feasibility Stage		Q2 2021-22

Development Stage		TBC following review

Validation Stage		TBC following review

Notes and commentary

## PS6-Efficiency_of_delivery
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS6: Achieving efficient delivery
Performance specification
	Source of Target		Actual (£bn)	Annual forecast milestone (£bn)	KPI/PI	Difference (Actual vs Target)	Notes
KPIs

Total efficiency
The value of operational and capital expenditure efficiency achieved by the end of Road Period 2.
Target: Demonstrate efficiency of £2.230 bn of capital and operational expenditure by the end of Road Period 2.					The annual forecast milestones numbers will be updated annually in line with Delivery Plan update.
2020-21	EIMM	In-year:		£0.233	KPI
		Cumulative:	£0.000	£0.233	KPI	-£0.233
2021-22	EIMM	In-year:		£0.257	KPI
		Cumulative:	£0.000	£0.490	KPI	-£0.490
2022-23	EIMM	In-year:		£0.352	KPI
		Cumulative:	£0.000	£0.842	KPI	-£0.842
2023-24	EIMM	In-year:		£0.513	KPI
		Cumulative:	£0.000	£1.355	KPI	-£1.355
2024-25	Performance Specification	In-year:		£0.875	KPI
		Cumulative:	£0.000	£2.230	KPI	-£2.230
Annual				Cumulative

PIs

Cost performance index and Schedule performance index / Progress of schemes in construction through reporting Cost performance index (CPI) and Schedule performance index (SPI).
Cost Performance Index
2020-21	Performance Specification		table	N/A	PI	N/A

Schedule Performance Index
2020-21	Performance Specification		table	N/A	PI	N/A

Commitments

Investigate and look to develop new or improved metrics to monitor cost and schedule for enhancement scheme development and construction, engaging with ORR.

6.1 Investigate & look to develop new or improved metrics to monitor cost & schedule for enhancement scheme development & construction, engaging with ORR
OMM Stages	Milestone

Concept Stage	Q3 2020-21

Feasibility Stage	Q2 2021-22

Development Stage	TBC following review

Validation Stage	TBC following review

Notes and commentary

## IP1
Statement IP1: Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
Highways England Delivery Plan - Major Improvements
Milestone Definitions and Key:
Construction Phase - Start of Works - the date when the start of the works is declared, following approval of final business case and construction budget, award of contract is in place along with completion of “Notice to proceed” and where applicable the “Notice to Treat”. Physical construction works will be evident on site.
Construction Phase - Open for Traffic - the date when the public will benefit from the improvements, in some instances residual works on the verges and off site will continue including some potential over night closures to finalise certain elements.
Delivery Plan Commitment - the date committed to in Highways England's 2020-2025 delivery plan.
Actual Achieved - the actual date that has been achieved.

	Region	Map Ref	Scheme Name	Construction Phase
				Start of Works		Open for Traffic
				Delivery Plan Commitment	Actual Achieved	Delivery Plan Commitment	Actual Achieved	Lane miles delivered (Actual)
Highways England schemes	North East	1	A1 Scotswood to North Brunton
		2	A19 Testos
		3	A19 Norton to Wynyard
		4	M621 Junctions 1-7
		5	A61 Westwood Roundabout
		6	A1 Morpeth to Ellingham
		7	A1 Birtley to Coal House
		8	A19 Down Hill Lane
		9	A63 Castle Street
		10	M62 Junctions 25-30
	North West	11	A585 Windy Harbour to Skippool
		12	M62 Junctions 20-25
		13	M6 Junction 19
		14	A66 Northern Trans-Pennine
		15	A5036 Princess Way
		16	M6 Junctions 21a-26
		17	Mottram Moor Link Road & A57 Link Road
		18	M56 Junctions 6-8
		19	M60/M62/M66 Simister Island Interchange
	Midlands	20	A500 Etruria
		21	M6 Junctions 13-15
		22	M42 Junction 6
		23	A46 Coventry Junctions
		24	M40/M42 Interchange
		25	A45/A6 Chowns Mill Junction
		26	M1 Junctions 13-19
		27	A38 Derby Junctions
		28	M54-M6 Link Road
		29	A5 Dodwells to Longshoot
		30	A52 Nottingham Junctions
		31	M6 Junction 10
		32	A46 Newark Bypass
		33	M42 Junctions 4-7
		34	M6 Junctions 4-5
		35	M6 Junctions 5-8
		36	M6 Junctions 8-10a
	East	37	A14 Cambridge to Huntingdon
		38	A47 Wansford to Sutton
		39	A47 Great Yarmouth Junctions
		40	A47 Guyhirn Junction
		41	A47 North Tuddenham to Easton
		42	A47 Thickthorn Junction
		43	A47 Blofield to North Burlingham
		44	A428 Black Cat to Caxton Gibbet
		45	A12 Chelmsford to A120
		46	M1 Junctions 10-13
	South East	47	M4 Junctions 3-12
		48	A34 Newbury to Oxford Enhancements
		49	M3 Junctions 9-14
		50	M27 Junctions 4-11
		51	M25 Junction 25
		52	M25 Junction 28
		53	M25 Junctions 10-16
		54	M25 Junction 10
		55	M3 Junction 9
		56	M27 Southampton Junction 8
		57	A27 Arundel Bypass
		58	A27 Worthing and Lancing improvements
		59	A31 Ringwood
		60	A2 Bean and Ebbsfleet
		61	M2 Junction 5
		62	A27 East of Lewes Package
		63	Lower Thames Crossing
	South West	64	A303 Sparkford to Ilchester
		65	A303 Amesbury to Berwick Down
		66	A358 Taunton to Southfields
		67	A30 Chiverton to Carland Cross
		68	A417 Air Balloon
		69	M4 Junctions 19-20 and M5 Junctions 16-17

These schemes will be delivered by local authorities with our support and are subject to future planning decisions.

External Delivery Organisation	Region	Map Ref	Scheme Name	Construction Phase
				Start of Works		Open for Traffic
				Delivery Plan Commitment	Actual Achieved	Delivery Plan Commitment	Actual Achieved
Housing infrastructure fund schemes	East	n/a	A120: Tendring/Colchester Border Garden Community
	South West	n/a	M5 junction 10 and link road
	South East	n/a	A249: Swale transport infrastructure
	North West	n/a	M6: South Lancaster Growth Catalyst – junction 33a

Third party schemes	Midlands	n/a	A5 Towcester relief road
	East	n/a	M11 junction 7a
	North West	n/a	M55 junction 2
	North West	n/a	M62 junction 19

## IP2
Statement IP2: RIS 3 Development Pipeline
No. schemes started development - total number of schemes that have started development nationally between April 2020 - March 2021
Programme level commentary - description of progress made at a national level across the RIS3 Development pipeline between April 2020 - March 2021

Region	RIS 3 Development Pipeline	Programme (National) level update

		No. schemes started development	Programme level commentary
North	A19 North of Newcastle Junctions	0	[TEXT]
	A64 Hopgrove
	M1 Leeds Eastern gateway
	M1/M62 Lofthouse interchange
	M6 Junctions 19 to 21a Knutsford to Croft extra capacity
	M1 Junctions 35 to 39 Sheffield to Wakefield extra capacity
	A1 Doncaster to Darrington
	M6 junction 22
	Manchester South East junction improvements
East	A47/A1101 Elm Road junction
	A11 Fiveways junction
	M11 junction 13 Cambridge West
	A12/A14 Copdock interchange
	A120 Braintree to A12
	Tilbury link road
Midlands	M6 junction 15 Potteries southern access
	A483 Pant-Llanymynech bypass (in cooperation with the Welsh Government)
	M1 North Leicestershire extra capacity
	M1 Leicester Western access
	A5 Hinckley to Tamworth
South and West	Severn resilience package
	A404 Bisham junction
	A2 Brenley Corner
	A303 Phase 2 upgrade
	A3/A247 Ripley South
	A21 safety package
	A2 Dover Access
	A27 Lewes to Polegate
	A27 Chichester improvements
	M27 South and Westhampton access
	A38 Trerulefoot-Carkeel safety package
	A404/M40 junction 4 High Wycombe

## IP3
Statement IP3: Designated funds
There are 4 designated funds outlined in Highways England's Delivery Plan 2020-2025: / 1. Safety and congestion - Safety and Congestion schemes / 2. User and communities - Integration; Walkers, Cyclists & Horse Riders; Roadside Facilities; Communities; Frieght and Information / 3. Environment and wellbeing - Biodiversity; Noise; Air quality; Flooding; Water Quality; Carbon; Cultural Heritage; Landscape and Environmental Legacy / 4. Innovation and modernisation - Design, construction and maintenance; Connected and Autonomous Vehicles; Customer Mobility; Energy and Environment; Operations. / Under each designated fund there are individual themes. Projects which use designated funds are aligned to a fund and an individual theme.
Key Definitions: / No. planned projects completing either feasibility, detailed design or implementation 2020-2021 - The combined number of projects planned to complete either the feasibility, detailed design or implementation stage for each fund / Feasibility - The number of projects that have completed the feasibility stage at the end of the year / Detailed design - The number of projects that have completed the detailed design stage at the end of the year / Implementation - The number of projects that have completed the implementation stage at the end of the year / Comments - Justification for any deviation or any supporting commentary

Fund	Projects planned 2020-2021	Projects delivered 2020-2021			Comments
	No. planned projects completing either feasibility, detailed design or implementation	Feasibility	Detailed design	Implementation
Safety and congestion fund
	0	0	0	0	[TEXT]
Users and communities fund
	0	0	0	0	[TEXT]
Environment and wellbeing fund
	0	0	0	0	[TEXT]
Innovation and modernisation fund
	0	0	0	0	[TEXT]

## IP4
Statement IP4: Renewal Volume Reporting
This statement details Highways England’s capital renewals delivery performance against planned volumes of activity associated with different asset types and interventions across the Strategic Road Network in 2020-21 (as set out in HE’s annual Delivery Plan).

	Asset	Description	Unit	2020-21
				Full year Actual
				Total	Baseline	Variance	Comments
Primary Elements	Asphalt road surface (pavement)	Total length of existing asphalt resurfaced	Lane miles		929
	Concrete road surface (pavement)	Total length of existing concrete road surface reconstructed and replaced with asphalt surface	Lane miles		7.5
	Safety barriers (steel)	Total length of steel safety barriers installed or renewed	Miles		89
	Safety barriers (concrete)	Total length of concrete safety barriers installed or renewed	Miles		2.5
	Significant structures	Number of significant structures	Number		44
Secondary Elements	Road markings	Length along the centre line of the road markings, including marking on new or replacement road surfacing	Linear metres		3450000
	Kerbs	Total length of kerbs laid or renewed	Linear metres		20500
	Safety barriers (steel)	Total length of steel safety barriers installed or renewed	Linear metres		143000
	Safety barriers (concrete)	Total length of concrete safety barriers installed or renewed	Linear metres		4000
	Drainage	Total length of drainage installed or renewed	Linear metres		98000
	Geotechnical	Total length of embankment / cutting treated parallel to the carriageway	Linear metres		3000
	Traffic signs (non-electrical)	Number of permanent non-electrical traffic signs installed or replaced	Number		475
	Guardrail	Total length of new or replacement pedestrian guardrail	Linear metres		2300
	Boundary fencing	Total length of new or replacement boundary fencing	Linear metres		80000
	Lighting	Number of road lighting columns installed or replaced	Number		1300
	Bridge joint	Number of bridge deck expansion joint installations installed or renewed	Number		525
	Bridge bearing	Number of bridge bearing units installed or renewed	Number		110
	Parapet	Total length of vehicle parapet installed or renewed	Linear metres		4750
	Waterproofing	Total surface area treated for waterproofing	Square metres		28000
	Motorway communications equipment	Number of new or replaced motorway communications equipment items	Number		150
	Technology renewals	Number of technology assets renewed or improved	Number		325

## IP5
Statement IP5: Maintenance Delivery Reporting
This statement details Highways England’s 2020-21 performance against a set of key maintenance activity measures. They represent a combination of planned, cyclical and reactive maintenance activities. The purpose of the statement is to provide supplementary reporting and assurance, in addition to the asset KPI’s and PI’s, that Highways England is keeping the network in good condition and meeting the requirements of the Licence to operate a safe and serviceable network.

Activity	Type	% Completed 24 Hour Priority Defects within the required timescale	% Completed within the required timescale	Comments
Defects	Paved area defects
	Road Markings and Road Studs defects
	Vehicle Restraint Systems defects
	Lighting defects
	Sign defects
	Soft estate defects (AD Areas)
	Reactive sweeping and cleaning actions (excluding graffiti) are completed (AD Areas)
	Sweeping and Cleaning - offensive graffiti
	Fences - defects identified related to safety
	Drainage asset defects (AD Areas)
	Geotechnical asset defects (AD Areas)
	Structures defects (AD Areas)
Activity	Type	% completed		Comments
Winter Service	The percentage of precautionary salting delivered within the precautionary salting and turnaround time as stated within the Severe Weather Plan
	Percentage of instances where running lanes were available in accordance with the Service Provider Severe Weather Plan in relation to snow clearance.
Activity	Type	% of total catchment length with a low risk status		Comments
Drainage	Drainage Performance Indicator
Activity	Type	% of planned litter clearance completed		Comments
Litter	Percentage of planned litter clearance activities undertaken in accordance with ASC requirements or the accepted programme set out in ADAMr (AD)
Activity	Type	% of cyclic works completed		Comments
Cyclical Maintenance / (AD Areas only)	Percentage of Cyclic works that are completed within the required timescales
Activity	Type	% of <24hr reactive works completed		Comments
Reactive Maintenance / (AD Areas only)	Percentage of Reactive <24hr works that are completed within the required timescales
Activity	Type	Total No of claims		Comments
Red Claims	Total number of claims
		Total No of settled claims		Comments
	Total number of settled claims
Green Claims	Total number of claims
		Total No of settled claims		Comments
	Total number of settled claims
Activity	Type	% of programme completed		Comments
Planned Asset Condition Inspections	Structures
	VRS
	Lighting
	Geotech
	Traffic Signs & Technology

## F1
Statement F1: Total income and expenditure

	RP1	2020-21				Baseline
	Actual	Forecast	Budget	Budget Difference		2020-21	2021-22	2022-23	2023-24	2024-25	RIS2 Total
Resource expenditure					** Note: HE is not funded at individual line level and these are HE working assumptions which could change annually
Operations and Maintenance (B1, B2, B3)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Private Finance Initiative (PFI) payments (B5)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Corporate Support (C1)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Business Services (C2)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Protocols (D1)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Total resource expenditure	0.0	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Capital expenditure
RIS1 Enhancements (A1)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
RIS 2 Enhancements (A2)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
RIS3 Development (A3)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Designated Funds (A4)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Other capital expenditure (A5)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Operations (B1, B2)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Maintenance and Renewals (B3)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Business Costs (C1, C2)		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Total capital expenditure	0.0	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Total expenditure	0.0	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0

Resource Expenditure by Type
Income	0.0	0.0	0.0	0.0
Pay	0.0	0.0	0.0	0.0
Non-Pay	0.0	0.0	0.0	0.0
Projects	0.0	0.0	0.0	0.0
Total resource expenditure	0.0	0.0	0.0	0.0

Commentary:
[INSERT COMMENTARY HERE]

## F2
Statement F2: Regional resource income and expenditure

£m	2020-21
	Actual	Budget	Budget Difference
Operations and Maintenance (B1, B2, B3)
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
Private Finance Initiative (PFI) payments (B5)
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
Corporate Support (C1)
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
Business Services (C2)
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
Protocols (D1)
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
Total	0.0	0.0	0.0

Commentary:
[INSERT COMMENTARY HERE]

## F2_1
Statement F2.1: Resource income and projects expenditure

£m		2020-21
		Forecast	Budget	Budget Difference
Operations and Maintenance (B1, B2, B3)
Non-projects	Pay	0.0	0.0	0.0
	Non-pay	0.0	0.0	0.0
	Income	0.0	0.0	0.0
	Non-projects Subtotal	0.0	0.0	0.0

Projects - Maintenance and Renewals	Routine Maintenance	0.0	0.0	0.0
	Winter Maintenance	0.0	0.0	0.0
	Technology - Maintenance	0.0	0.0	0.0
	Renewal of Roads	0.0	0.0	0.0
	Renewal of Structures	0.0	0.0	0.0
	Other Maintenance	0.0	0.0	0.0
Projects - General Operations	S274/S278 Works	0.0	0.0	0.0
	Technology	0.0	0.0	0.0
	Other	0.0	0.0	0.0
Projects - Customer Operations	Traffic Management	0.0	0.0	0.0
	Traffic Officer Service	0.0	0.0	0.0
	Projects Subtotal	0.0	0.0	0.0
	Total	0.0	0.0	0.0
PFI (Private Finance Initiative)
Non-projects	Pay	0.0	0.0	0.0
	Non-pay	0.0	0.0	0.0
	Income	0.0	0.0	0.0
	Non-projects Subtotal	0.0	0.0	0.0

Projects	A1(M) Darrington to Dishforth	0.0	0.0	0.0
	A19 Dishforth to Tyne Tunnel	0.0	0.0	0.0
	A249 Iwade to Queenborough	0.0	0.0	0.0
	A30/A35 Exeter to Bere Regis	0.0	0.0	0.0
	A419/A417 Swindon to Gloucester	0.0	0.0	0.0
	A50/A564 Stoke - Derby link	0.0	0.0	0.0
	A69 Carlisle to Newcastle	0.0	0.0	0.0
	M1-A1 Yorkshire link	0.0	0.0	0.0
	M25 London Orbital Motorway contract	0.0	0.0	0.0
	M40 Junctions 1-15	0.0	0.0	0.0
	Other	0.0	0.0	0.0
	Projects Subtotal	0.0	0.0	0.0
	Total	0.0	0.0	0.0
Corporate Support (C1)
Non-projects	Pay	0.0	0.0	0.0
	Non-pay	0.0	0.0	0.0
	Income	0.0	0.0	0.0
	Non-projects Subtotal	0.0	0.0	0.0

Projects	Lands	0.0	0.0	0.0
	Other	0.0	0.0	0.0
	Projects Subtotal	0.0	0.0	0.0
	Total	0.0	0.0	0.0
Business Services (C2)
Non-projects	Pay	0.0	0.0	0.0
	Non-pay	0.0	0.0	0.0
	Income	0.0	0.0	0.0
	Non-projects Subtotal	0.0	0.0	0.0

Projects	Research and Development	0.0	0.0	0.0
	Other	0.0	0.0	0.0
	Projects Subtotal	0.0	0.0	0.0
	Total	0.0	0.0	0.0
Protocols (D1)
Non-projects	Pay	0.0	0.0	0.0
	Non-pay	0.0	0.0	0.0
	Income	0.0	0.0	0.0
	Non-projects Subtotal	0.0	0.0	0.0

Projects		0.0	0.0	0.0
	Projects Subtotal	0.0	0.0	0.0
	Total	0.0	0.0	0.0
	Total resource expenditure	0.0	0.0	0.0

## F2_2
Statement F2.2: Analysis of protocols expenditure

	2020-21					2015-16	2016/17	2017-18	2018-19	2019-20	RIS 1 Total
	Actual	Budget	Budget Difference			Baseline v1.1	Baseline v1.1	Baseline v1.1	Baseline v1.1	Baseline v1.1	Baseline v1.1
Abnormal Loads	0.0	0.0	0.0			1.1	1.2	1.2	1.2	1.2	5.9
Dart Charge	0.0	0.0	0.0			26.2	26.9	27.5	27.5	28.2	136.4
M6 Toll	0.0	0.0	0.0			0.0	0.0	0.0	0.0	0.0	0.2
Historical Railways Estate	0.0	0.0	0.0			7.2	7.4	7.5	7.5	7.7	37.3
National Salt Reserve	0.0	0.0	0.0			0.9	0.9	0.9	0.9	1.0	4.7
Severn Crossings up to the end of the concession	0.0	0.0	0.0			1.9	2.0	2.0	2.0	2.1	10.0
Technical Regulations	0.0	0.0	0.0			1.6	1.7	1.7	1.7	1.8	8.5
Total Protocols Expenditure	0.0	0.0	0.0			39.0	40.0	41.0	41.0	42.0	203.0

## F2_3
Statement F2.3: Analysis of FTE expenditure

	2020-21					2015-16	2016/17	2017-18	2018-19	2019-20	RIS 1 Total
	Actual	Budget	Budget Difference			Baseline v1.1	Baseline v1.1	Baseline v1.1	Baseline v1.1	Baseline v1.1	Baseline v1.1
Centrally Managed	0.0	0.0	0.0			1.1	1.2	1.2	1.2	1.2	5.9
Commercial and Procurement	0.0	0.0	0.0			26.2	26.9	27.5	27.5	28.2	136.4
Communications Directorate	0.0	0.0	0.0			0.0	0.0	0.0	0.0	0.0	0.2
Finance and Business Services	0.0	0.0	0.0			7.2	7.4	7.5	7.5	7.7	37.3
Human Resources	0.0	0.0	0.0			0.9	0.9	0.9	0.9	1.0	4.7
Major Projects	0.0	0.0	0.0			1.9	2.0	2.0	2.0	2.1	10.0
Operations	0.0	0.0	0.0			1.6	1.7	1.7	1.7	1.8	8.5
Information Technology Directorate	0.0	0.0	0.0
Safety, Engineering and Standards	0.0	0.0	0.0
Strategy and Planning	0.0	0.0	0.0
General Counsel	0.0	0.0	0.0
FTE Total	0.0	0.0	0.0			39.0	40.0	41.0	41.0	42.0	203.0

	2020-21
	Actual	Budget	Budget Difference
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
FTE Total	0.0	0.0	0.0

## F3
Statement F3: Capital expenditure

£m	Activity	2020-21				Baseline
		FYF	Budget	Budget Difference		2020-21	2021-22	2022-23	2023-24	2024-25	RIS2 Total
Maintenance and Renewals
	Renewal of Roads	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Renewal of Structures	0.0	0.0	0.0
	Renewal of Technology	0.0	0.0	0.0
	Winter Maintenance - Assets	0.0	0.0	0.0
	Total Maintenance and Renewals	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
RIS1 Enhancements
	Regional Investment Programme	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Smart Motorways Programme	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Complex Infrastructure Programme	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Other RIS1 expenditure including Portfolio Risk/Contingency and Surplus Funding	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Total RIS1 Enhancements	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
RIS2 Enhancements
	Regional Investment Programme	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Smart Motorways Programme	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Complex Infrastructure Programme	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Other RIS2 expenditure including Portfolio Risk/Contingency	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Total RIS2 Enhancements	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
RIS3 Development
		0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
					0.0	0.0	0.0	0.0	0.0	0.0

					0.0	0.0	0.0	0.0	0.0	0.0
					0.0	0.0	0.0	0.0	0.0	0.0

					0.0	0.0	0.0	0.0	0.0	0.0
	Total RIS3 Development	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Designated Funds
	Environment and Wellbeing	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Innovation and Modernisation	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Safety and Congestion Fund	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Users and Communities	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
				0.0		0.0	0.0	0.0	0.0	0.0	0.0
				0.0		0.0	0.0	0.0	0.0	0.0	0.0
				0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Total Designated Funds	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
Operations, Business Costs and Other Capital
	Operations	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Business Costs	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Other Capital	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0
	Total Operations, Business Costs and Other Capital	0.0	0.0	0.0		0.0	0.0	0.0	0.0	0.0	0.0

Commentary:
[INSERT COMMENTARY HERE]

## F3_1
Statement F3.1 : Enhancement expenditure

£m	Scheme name	2020-21
		FYF	Budget	Budget Difference
RIS1 Enhancements
	A1 Birtley to Coal House	0.0	0.0	0.0
	A1 Morpeth to Ellingham and A1 North of Ellingham	0.0	0.0	0.0
	A1 Scotswood to North Brunton	0.0	0.0	0.0
	A1(M) Junctions 6-8	0.0	0.0	0.0
	A12 Chelmsford to A120	0.0	0.0	0.0
	A14 Cambridge to Huntingdon	0.0	0.0	0.0
	A19 Down Hill Lane	0.0	0.0	0.0
	A19 Norton to Wynyard	0.0	0.0	0.0
	A19 Testos	0.0	0.0	0.0
	A2 Bean and Ebbsfleet	0.0	0.0	0.0
	A27 Arundel Bypass	0.0	0.0	0.0
	A27 East of Lewes Package	0.0	0.0	0.0
	A27 Worthing and Lancing improvements	0.0	0.0	0.0
	A30 Chiverton to Carland Cross	0.0	0.0	0.0
	A303 Amesbury to Berwick Down	0.0	0.0	0.0
	A303 Sparkford to Ilchester	0.0	0.0	0.0
	A31 Ringwood	0.0	0.0	0.0
	A34 Newbury to Oxford Enhancements	0.0	0.0	0.0
	A358 Taunton to Southfields	0.0	0.0	0.0
	A38 Derby Junctions	0.0	0.0	0.0
	A428 Black Cat to Caxton Gibbet	0.0	0.0	0.0
	A45/A6 Chowns Mill Junction	0.0	0.0	0.0
	A46 Coventry Junctions	0.0	0.0	0.0
	A47 Blofield to North Burlingham	0.0	0.0	0.0
	A47 Great Yarmouth Junctions	0.0	0.0	0.0
	A47 Guyhirn Junction	0.0	0.0	0.0
	A47 North Tuddenham to Easton	0.0	0.0	0.0
	A47 Thickthorn Junction	0.0	0.0	0.0
	A47 Wansford to Sutton	0.0	0.0	0.0
	A5 Dodwells to Longshoot	0.0	0.0	0.0
	A500 Etruria	0.0	0.0	0.0
	A5036 Princess Way	0.0	0.0	0.0
	A52 Nottingham Junctions	0.0	0.0	0.0
	A585 Windy Harbour to Skippool	0.0	0.0	0.0
	A61 Westwood Roundabout	0.0	0.0	0.0
	A63 Castle Street	0.0	0.0	0.0
	M1 Junctions 13-19	0.0	0.0	0.0
	M2 Junction 5	0.0	0.0	0.0
	M20 Junction 10a	0.0	0.0	0.0
	M20 Junctions 3-5	0.0	0.0	0.0
	M23 Junctions 8-10	0.0	0.0	0.0
	M25 Junction 10	0.0	0.0	0.0
	M25 Junction 25	0.0	0.0	0.0
	M25 Junction 28	0.0	0.0	0.0
	M25 Junctions 10-16	0.0	0.0	0.0
	M27 Junctions 4-11	0.0	0.0	0.0
	M27 Southampton Junction 8	0.0	0.0	0.0
	M271/A35 Redbridge Roundabout Upgrade	0.0	0.0	0.0
	M3 Junction 9	0.0	0.0	0.0
	M3 Junctions 9-14	0.0	0.0	0.0
	M4 Junctions 3-12	0.0	0.0	0.0
	M40/M42 Interchange	0.0	0.0	0.0
	M42 Junction 6	0.0	0.0	0.0
	M49 Avonmouth Junction	0.0	0.0	0.0
	M54-M6 Link Road	0.0	0.0	0.0
	M56 Junctions 6-8	0.0	0.0	0.0
	M6 Junction 10	0.0	0.0	0.0
	M6 Junction 19	0.0	0.0	0.0
	M6 Junctions 13-15	0.0	0.0	0.0
	M6 Junctions 21a-26	0.0	0.0	0.0
	M6 Junctions 2-4	0.0	0.0	0.0
	M62 Junctions 10-12	0.0	0.0	0.0
	M62 Junctions 20-25	0.0	0.0	0.0
	M621 Junctions 1-7	0.0	0.0	0.0
	Mottram Moor Link Road & A57 Link Road	0.0	0.0	0.0
	M62 Junctions 25-30	0.0	0.0	0.0
	A47 Great Yarmouth Junctions	0.0	0.0	0.0
	A1 Coal House to Metro Centre	0.0	0.0	0.0
	A1 Leeming to Barton	0.0	0.0	0.0
	M1 Junctions 28-31	0.0	0.0	0.0
	A14 Kettering bypass widening	0.0	0.0	0.0
	M1 Junction 19 improvement	0.0	0.0	0.0
	A45-A46 Tollbar End	0.0	0.0	0.0
	A5/M1 junction 11a Link	0.0	0.0	0.0
	M6 Junctions 10a-13	0.0	0.0	0.0
	M1 junctions 32-35A	0.0	0.0	0.0
	M3 junctions 2-4A	0.0	0.0	0.0
	A160/A180 Immingham	0.0	0.0	0.0
	A21 Tonbridge to Pembury	0.0	0.0	0.0
	M5 junctions 4A-6	0.0	0.0	0.0
	M6 junctions 16-19	0.0	0.0	0.0
	A19/A1058 Coast Road	0.0	0.0	0.0
	M1 junctions 24-25	0.0	0.0	0.0
	M1 junction 45 Improvement	0.0	0.0	0.0
	M56 new junction 11A	0.0	0.0	0.0
	M1 junctions 23A-24	0.0	0.0	0.0
	A1(M) junctions 6- 8 smart motorway	0.0	0.0	0.0
	A556 Knutsford to Bowdon	0.0	0.0	0.0
	A453 Widening	0.0	0.0	0.0
	M25 Junction 30	0.0	0.0	0.0
	M1 junctions 39-42	0.0	0.0	0.0
	A43 Abthorpe junction	0.0	0.0	0.0
	M11 junction 7a upgrade	0.0	0.0	0.0
	M3 junction 10-11 improved sliproads	0.0	0.0	0.0
	M3 junction 12 -14 improved sliproads	0.0	0.0	0.0
	A5 Towcester relief road	0.0	0.0	0.0
	A50 Uttoxeter (Project A)	0.0	0.0	0.0
	Other RIS1 expenditure including Portfolio Risk/Contingency and Surpus Funding	0.0	0.0	0.0
	Total RIS1 Enhancements	0.0	0.0	0.0
RIS2 Enhancements
	A46 Newark Bypass	0.0	0.0	0.0
	A417 Air Balloon	0.0	0.0	0.0
	M60/M62/M66 Simister Island Interchange	0.0	0.0	0.0
	Lower Thames Crossing and Lower Thames Crossing Top Up	0.0	0.0	0.0
	A66 Northern Trans-Pennine	0.0	0.0	0.0
	A34 North and South of Oxford	0.0	0.0	0.0
	Oxford to Cambridge Expressway	0.0	0.0	0.0
	M42 Junctions 4-7	0.0	0.0	0.0
	M6 Junctions 4-5	0.0	0.0	0.0
	M6 Junctions 5-8	0.0	0.0	0.0
	M6 Junctions 8-10a	0.0	0.0	0.0
	M1 Junctions 10-13 retrofit	0.0	0.0	0.0
	M62 Junctions 25-30 retrofit	0.0	0.0	0.0
	M6 Junctions 19-21A	0.0	0.0	0.0
	Other RIS2 expenditure including Portfolio Risk/Contingency	0.0	0.0	0.0
	Total RIS2 Enhancements	0.0	0.0	0.0

## F3_2
Statement F3.2: Regional capital income and expenditure

£m	2020-21
	FYF	Budget	Budget Difference
Maintenance & Renewals
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
RIS1 Enhancements
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
RIS2 Enhancements
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
RIS3 Development
Centrally managed	0.0	0.0	0.0
East
Midlands
North West
South East
South West
Yorkshire & North East
Subtotal	0.0	0.0	0.0
Designated Funds
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
Operations, Business Costs, and Other Capital
Centrally managed	0.0	0.0	0.0
East	0.0	0.0	0.0
Midlands	0.0	0.0	0.0
North West	0.0	0.0	0.0
South East	0.0	0.0	0.0
South West	0.0	0.0	0.0
Yorkshire & North East	0.0	0.0	0.0
Subtotal	0.0	0.0	0.0
Total	0.0	0.0	0.0

Commentary:
[INSERT COMMENTARY HERE]

## 'http://www.rail-reg.gov.uk/Documents%20and%20Settings/Gupi/Local%20Settings/Temporary%20Internet%20Files/Content.IE5/4X8RKIN3/ORR-#322227-v16-Financial_Model_GB_-_OCT08_Final_Determination.XLS'#Assumptions_GB1
				4

				1

				3

Renewals					2
Amortisation
Manual input
				2
				Exclude indexation
				1

				0
				Semi Annual Interest
				1
				Baseline

				1

				2

## 'http://www.rail-reg.gov.uk/Documents%20and%20Settings/Gupi/Local%20Settings/Temporary%20Internet%20Files/Content.IE5/4X8RKIN3/ORR-#322227-v16-Financial_Model_GB_-_OCT08_Final_Determination.XLS'#Inputs_GB1
3923.2018510810303

## 'http://www.rail-reg.gov.uk/Documents%20and%20Settings/Gupi/Local%20Settings/Temporary%20Internet%20Files/Content.IE5/4X8RKIN3/ORR-#322227-v16-Financial_Model_GB_-_OCT08_Final_Determination.XLS'#Assumptions_GB
4

## 'http://www.rail-reg.gov.uk/Documents%20and%20Settings/Gupi/Local%20Settings/Temporary%20Internet%20Files/Content.IE5/4X8RKIN3/ORR-#322227-v16-Financial_Model_GB_-_OCT08_Final_Determination.XLS'#Inputs_GB
3923.2018510810303

## 'file://oasisdata6/homedirs/Program%20Files/FileNET/IDM/Cache/2003012410152300001/all%20the%20charts.xls'#Figure_1_11
35877

## 'file://oasisdata6/homedirs/Program%20Files/FileNET/IDM/Cache/2003012410152300001/all%20the%20charts.xls'#4_6_ten_year_bonds1
35877			33091			33092			33973			34096

## 'file://oasisdata6/homedirs/Program%20Files/FileNET/IDM/Cache/2003012410152300001/all%20the%20charts.xls'#4_6_ten_year_bonds
35877

## 'http://share/Users/Metcar/AppData/Local/Temp/788f9865-dbc7-4478-a75a-97db95b8f085/160405_Year-end_reporting_-_IP3_Designated_Funds_template.xlsm'#table
Making the network safer
Improving user satisfaction
Supporting the smooth flow of traffic
Encouraging economic growth
Delivering better environmental outcomes
Helping cyclists walkers and other vulnerable users of the Network
Achieving real efficiency
Keeping the network in good condition
Detailed analysis of enhancement monitoring milestones dates
Strategic studies deliverables
Ring fenced investment funds
Renewal volume reporting
Maintenance delivery reporting
Total income and expenditure
Resource Income and expenditure
Regional resource income and expenditure
Maintenance resource income and expenditure
Renewals resource income and expenditure
Private Finance Initiative (PFI) income and expenditure
General operations income and expenditure
Traffic management resource income and expenditure
Support costs
Other project activities income and expenditure
Capital expenditure
Regional capital income and expenditure
Analysis of protocols expenditure
Maintenance unit costs and volumes
Renewals unit costs and volumes
Effect of input price inflation

## 'file://Bpclus1/ap2000/AP2018/Quarterly%20and%20annual%20accounts/Q4/Accounts%20Model/HE%20Q4%2017_18%20Accounts%20Model%20(no%20links).xlsx'#VariableData
31 March 2018

year

## 'http://share/Users/eshaw/AppData/Local/Microsoft/Windows/Temporary%20Internet%20Files/Content.Outlook/UMZOFSXZ/2014-10-03%20cost%20info%20for%20all%206%20FS%20VERSION%20FOR%20HMT.xlsx'#Sheet1
Likely to be able to announce
May be able to announce - further verification necessary
Unlikely to be able to announce

## 'http://share/Users/lonem7/AppData/Local/Temp/Temp1_Products.zip/18%20Earned%20Value/BR02a_-_In_Year_Expenditure_(Current)_Report%20Apr15.xls'#Macro1
Recover